## Sheet1
SAFE WORK METHOD STATEMENT & RISK ASSESSMENT
COMPANY DETAILS
| Company name: | Brisbane West Earthmoving | Contact name
| ACN/ABN: | 21154532475 | Contact number:
| Address: | PO Box 5068 Kenmore East QLD | Phone number: | (0406)443333
PROJECT DETAILS
| Project name: |  |  | Location:
Scope of Work: Use of Excavator, Bobcat, Truck and relevant attachments
| SWMS developed by:Brisbane West Earthmoving dated 02.05.2014 |  |  | Start date: / / 2014 Completion date: / / 2014 Duration of job:
| SWMS reviewed by:Brisbane West Earthmoving dated 02.05.2014 |  |  | SWMS approved by : :Brisbane West Earthmoving Date 02.05.2014
Mitch Lynton Manager
(Signed) for and on behalf of Brisbane West Earthmoving (Position)
Persons involved in the development of the SWMS and consultation acknowledgment. Work undertaken in line with Fatigue Management Policy for the business.
| Employee name | Signature |  | Date | Employee name |  | Signature |  |  | Date
|  | (I have been consulted in this SWMS) |  |  |  |  | (I have been consulted in this SWMS)
| Persons who will carry out task: (List all persons who will be working on site at any time). | Duties and responsibilities: (List details of trades and duties of specific personnel). | Signature: (All persons working on site are required to read fully and sign SWMS). | Persons who will carry out task: (List all persons who will be working on site at any time.) |  |  | Duties and responsibilities: (List details of trades and duties of specific personnel). |  | Signature: (All persons working on site are required to read fully and sign SWMS).
| SWMS NO.: |  | Project Name : |  |  |  | Location:
| Plant and equipment required: (List all plant and equipment to be used by contractor this for job). |  |  | Safety and maintenance checks required: (Provide details of maintenance schedules on high-risk plant, including testing of electrical equipment).
| Personal Protective Equipment (PPE) |  |  | N/A
| Excavator |  |  | Log Books, Pre Start Checks
| Backhoe |  |  | Log Books, Pre Start Checks
| Truck |  |  | Log Books, Pre Start Checks
| Engineering details / Certificates/Approvals required: (Provide details required for work listed as hazardous or requiring specific work methods, eg, demolition, formwork, falsework, tilt slab construction, etc). |  |  | Legislation / Standards / Codes of Practice applicable: (Ensure that work methods comply with or exceed legislated requirements or applicable Codes of Practice and that the relevant Codes, etc, are available on site).
| Excavation |  |  | Workplace Health & Safety Act 2011
Qld Workplace Health & Safety Regulation 2011
Managing Risk of Plant in the Workplace Code of Practice 2012
Hazardous Chemicals Code of Practice 2003
Managing Noise and Prevention of Hearing Loss at Work Code of Practice 2011
Electrical Safety Act 2002
Work Health & Safety Consultation, Co-operation and Co-ordination Code of Practice 2011
Managing the Risk of Falls at Workplaces Code of Practice 2011
Hazardous Manual Tasks Code of Practice 2011
Excavation Work Code of Practice 2012
Construction Work Code of Practice 2012
How to Manage and Control Asbestos in the Workplace Code of Practice 2011
| Qualifications / Certificates of Competency / Training / Experience |  |  | Details of licensed and qualified persons who will carry out specific tasks
| required to carry out task: (List details of qualifications, certificates, training and experience needed to carry out the tasks required). |  |  | Name | Type | Expiry Date |  | Name | Type | Expiry Date
Qld Transport Licence
White Card
O.H.S. Certification
| Induction |  |  | Contractor
| SWMS NO.: |  | Project Name : |  |  |  | Location:
Risk Level Matrix
| LEVEL OF CONSEQUENCES | CONSEQUENCES OF EVENT OCCURRING |  |  | LIKELIHOOD OF EVENT OCCURRING
|  | What is the likely outcome of an exposure to the risk? |  |  | Almost Certain |  | Likely | Possible | Unlikely | Rare
| Catastrophic | Fatality or permanent disability; toxic release of chemicals, long-term environmental impact; loss of facilities; very high $ loss |  |  | E |  | E | E | E | H
| Major | Long-term illness or serious injury; serious medium-term environmental effects; major property damage; loss of production; high $ loss |  |  | E |  | E | E | H | H
| Moderate | Medical treatment requiring up to several days off work; spillage contained with outside assistance; significant property damage; med – high $ loss |  |  | E |  | H | M | M | L
| Minor | Minor injury requiring First-Aid; spillage contained on site; moderate property damage; low-med. $ loss |  |  | H |  | H | M | L | L
| Insignificant | Minor injury requiring First-Aid; spillage contained on site; moderate property damage; low-med. $ loss |  |  | H |  | M | L | L | L
| LIKELIHOOD OF EVENT OCCURRING |  |  | DETERMINATION OF RISK CONTROL ACTIONS
| Almost certain | Event is expected to occur in most circumstances |  | Risk Score | Risk Level |  | Action Required
| Likely | Event will probably occur in most circumstances |  | E | Extreme |  | URGENT - Immediate action required to control risk.
| Possible | Event might occur at some time |  | H | High |  | Highest management decision required urgently.
| Unlikely | Event could occur at some time |  | M | Medium |  | Follow management instructions regarding risk.
| Rare | Event may occur only in exceptional circumstances |  | L | Low |  | These risks may not require immediate attention.
COMPILATION OF SWMS
| Step |  | Number each discrete step in the task in sequence – e.g., 1, 2, etc.
| Activity |  | Briefly describe the activity to be carried out in each step.
| Hazards |  | Identify what in each activity could cause harm to a person, the job, materials, or the environment.
| Risk(1) |  | The degree of risk posed by the hazard. (Use Risk Level Matrix to determine risk ranking before controls implemented).
| Risk Controls |  | What precautions or control measures must be taken to control the risk.
| Risk(2) |  | The degree of risk following implementation of risk controls (Use Risk Level Matrix to determine ranking of residual risk).
Person Responsible
SWMS NO.: |  |  | Project Name : |  |  |  | Location:
ACTIVITY |  |  | HAZARD(S)/RISK | RISK(1) | RISK CONTROL(S) |  |  |  | RISK(2) | PERSON
ESPONSIBLE
Break job down into discrete steps |  |  | Identify the hazards associated with each step, and examine each to identify possibilities that could lead to an accident | Refer to the risk matrix | Consider number of people required to carry out a task, training, skills and competencies required, licences, permits, etc, environmental controls, plant, tools and equipment, safety equipment and PPE, MSDS, etc. |  |  |  | Refer to the risk matrix | List (by name) those persons specificallyresponsible for this.
Each step should accomplish some major task and be in a logical sequence.
# | Example – Use high pressure water blaster to clean concrete walls |  | Injury from high pressure water jet and chemicals used for cleaning concrete | H | Erect barricade and signs to prevent entry of persons to work area |  |  |  | L | John Smith (L/H)
| before painting | [8 empty] | Joe Bloggs
Erect drift curtain to prevent spray drift into adjoining work areas.
Cleaning chemicals which pose least environmental risk to be used
Operator and assistants to wear safety goggles, face shield and gloves
Cover gully traps to prevent runoff of contaminated water into drains
1 | Selection of Vehicle |  | Overloading | E | Vehicle must have adequate load carrying capacity for the |  |  |  | M | Operator
|  |  | Overhanging load |  | proposed load. Vehicle loading must not exceed rated tyre and
axle capacity of vehicle. Vehicle must have sufficient space for
the load on tray for whole of load. Do not exceed legal mass
limits. Do not exceed GCM of vehicle. Ensure correct weight
distribution
2 | Positioning of loads |  | Uneven/excess axle loads | H | Position load to maintain stability, steering and braking. |  |  |  | M | Operator
|  |  | Loss of stability or control |  | Loads should not overload tyres and axles.
Place heavy objects between axles and provide even loading
across tray. Loads offset to one side of vehicle will affect
stability of turning vehicle. Place heavy loads lower (on tray) to
reduce overturning moment. Loads must be restrained to
prevent shifting whilst vehicle in motion.
3 | Tall or High loads |  | Overturning | E | High centre of gravity of load will result in higher overturning |  |  |  | M | Operator
|  |  | Striking overhead objects |  | risk. Use low loader or drop deck trailer, etc, for high or tall
loads. Check overall height of loaded vehicle to ensure that it
does not exceed height restrictions on proposed route or legal
height limits (gen. 4.3m.) Check weight of all loads. Reduce
speed for high loads. Special permit may be required to
transport over-height loads.
4 | Selection of restraints |  | Load Slipping | H | Higher tension in restraints allows loads to be held more |  |  |  | M | Operator
|  |  | Load capacity of restraints |  | effectively. Size, weight and shape of load must be considered
when selecting restraints. Use additional restraints where type
of lashing has a lower load capacity. Do not overload restraints.
Bends over corners and angles of lashing must be considered.
5 | Rope Lashings |  | Loosening during |  | Transport fibre rope only must be used for lashing purposes. |  |  |  |  | Operator
|  |  | transport |  | Rope is colour coded for its lashing capacity (12mm transport
|  |  | Damage to load |  | rope with two black markers = 100kg 6lashing capacity, 12mm
with 1 yellow and 1 black marker= 300 kg lashing capacity).
Synthetic ropes must only be used to restrain lightweight
loads. Natural fibre ropes must not be used for transport
purposes.
6 | Chains |  | Transport Chain | E | Transport chain of at least 8mm diameter should be used to |  |  |  | M | Operator
lash loads. Protect chains from damage from sharp corners and
projections. Do not use unrated chain. Select chain to match
load.
7 | Drive to site |  | Traffic Road safety | M | Drivers will hold a current licence for the vehicle/plant they are |  |  |  | L | Operator
operating. Pre-start check will be completed daily. All
equipment, tools and material shall be secured. Unregistered
machinery and equipment must not be driven on a public
roadway unless a permit to do so has been obtained from the
relevant Traffic Authority.
8 | Competency Requirements |  | Competency of operators | L | Operators of earthmoving plant must hold the appropriate |  |  |  | L | Operator
licence. Excavator operator- Class LE.
FE Loader operator – Class LL Backhoe/loader operator- Class
LB.
9 | Security of site |  | Traffic | E | A worksite must be protected from passing traffic by the use of |  |  |  | M | Contractor
appropriate traffic controls, such as road closures (full or part),
detours or side-tracks, barricading and fencing, use of traffic
control devices (such as temporary road signs, traffic cones and
bollards, barriers, portable traffic lights, etc), and traffic
controllers (where a need to manually control traffic flows
through the worksite exists).
|  |  | Pedestrians | H | A safe path for pedestrians must be provided outside of the |  |  |  | M | Contractor
work area. A barricade or hoarding of at least 900mm must
be erected around an excavation unless it is not possible
or no members of the public are likely to be in the area of
the excavation.
If necessary, pedestrians may have to be diverted to the
other side of a road.
A safe means of crossing the road at each end of the closed
footpath must be provided.
10 | Inspection of site |  | Fit to operate plant | H | Ensure a standard work day for all work allocated across ALL |  |  |  | M | Operator
sites, in line with the Fatigue Management Policy for the
business. If the times are a breach of the policy then a Risk
Assessment must be undertaken prior to commencement of
work.
| Benching |  | Cave-in, flooding | H | A competent person is to inspect the site before excavation |  |  |  | M | Contractor
commences to assess any risk of cave-in or flooding of the
trench due to ground conditions. Trenches are to be inspected
at the commencement of work each day to ensure that the
trench is safe for a person to enter.
|  |  | Stability of structures | H | An excavation or trench where a person is required to enter |  |  |  | M | Contractor
should be shored or shielded, benched or battered to prevent
the collapse or cave-in. Benching – height not to exceed width,
and no vertical face to exceed 1.5 metres. Battering – angle not
to exceed 45° and bottom vertical face not to exceed 1.5
metres.
|  |  | Underground structures | H | Control measures necessary to prevent risk of collapse of |  |  |  | M | Contractor
|  |  | and services |  | adjoining structures (such as a building or road) are to be
identified before excavation commences and implemented
before the risk eventuates
| Battering |  | Fire Ants | H | The existence and location of underground services (such as |  |  |  | M | Contractor
water, gas, electricity, Telecommunications, etc) must be carried
out before any excavation of the site commences. Information
required before digging starts should include the types, numbers
and depths of the services. In cases where a risk of damage
exists, a representative of the utility concerned should be
requested to be present on site during the excavation. Dial ll00
before you dig. (Note: this is a free Australia-wide service for all
underground services). A written record of all requests,
responses and representations (including the names and
oppositions of persons) should be kept with the job records.
Underground essential services information obtained must be
made available to any worker, principal contractor and
subcontractors and readily available for inspection, as required
under the WHS Act. Must be retained until the excavation work
is completed or, if there is a notifiable incident relating to the
excavation work, 2 years after the incident occurs
|  |  | Asbestos | E | When 1 cubic metre of soil or more in a fire ant declared zone is |  |  |  | M | Contractor/
[5 empty] | to be excavated Dept of Primary Industries must attend prior to |  |  |  |  | Operator
commencement. For inspection bookings call Qld Dept of
Primary Industries on 13 25 23
| Combination of Both |  | Exposure to Hazardous | H | Where asbestos is identified, work shall cease immediately. |  |  |  | M | Contractor/
|  |  | Substances | H | Liaise with the contractor for further direction. All ACM removal |  |  |  | M | Operator
must be carried out in accordance with Section 7of the Code of
Practice for the Management of Asbestos in the Workplace.
Consult relevant state or territory OHS authority regarding
requirements for training, information to be provided, and health
monitoring of asbestos workers.
Obtain a current Safety Data Sheet (SDS) for each substance
to be used in a workplace before the substance is first used.
The MSDS must provide detailed information about the name of
the substance (including ingredients in mixtures, health hazard
information, precautions for use and safe handling of the
substance).
Provide a register which contains a SDS for each substance
together with a risk assessment in each area where a
substance is used
11 | Safety of persons on site |  | Traffic and mobile plant | H | Persons working in areas where traffic or mobile plant is |  |  |  | M | Contractor/
[5 empty] | or may be present are to be provided with and wear |  |  |  |  | Operator
suitable high-visibility garments.
Persons working in traffic areas at night are to be
provided with and wear suitable reflectorised garments
or safety vests.
|  |  | Risk of foot injury | H | Excavations and excavation sites will pose a high risk of foot |  |  |  | M | Operator
injury. Safety footwear must be worn.
Risk of head injury exists where plant or machinery,
power tools, or work below ground level is carried out.
|  |  | Falling/flying objects | H | Provide means to prevent objects falling into an excavation or |  |  |  | M | Contractor/
[5 empty] | trench. Safety footwear and head protection must be worn. |  |  |  |  | Operator
|  |  | Contaminated | H | Excavations and trenches adjacent to roadways may be |  |  |  | M | Operator/
|  |  | atmosphere |  | affected by gases from vehicle exhausts. |  |  |  |  | Contractor
|  |  | Collapse or cave-in | H | Excavated material should not be placed less than 600mm |  |  |  | M | Operator/
[5 empty] | from the edge of an excavation to minimise risk of collapse |  |  |  |  | Contractor
due to the weight of the spoil. An excavation where a
possibility of collapse or cave-in exists should be shored,
shielded, benched or battered to prevent the collapse or
cave-in
Excavated material and loads near excavations
Refer opposite
12 | Transport |  | Loading and Unloading | H | Ensure that area where loader is to be unloaded or loaded is |  |  |  | M | Operator
secured from traffic and pedestrians with barriers or cones,
etc, before commencing. Position truck or trailer to minimise
ramp slope, and apply park brake.
Load rubber tyred skid steer loader onto truck by reversing
slowly up ramp (rear of machine facing UP ramp), with
bucket in lowered position. Ensure that machine is secured
against movement, and that park brake is ON.
13 | Pre-Start checks |  | Roll-over protection | M | Tractors must be fitted with an approved roll-over protective |  |  |  | L | Operator
structure (ROPS) unless specifically exempted by the
appropriate statutory authority.
|  |  |  | H | Check fuel, hydraulic oil, engine oil, transmission oil, coolant |  |  |  | M | Operator
and battery. Check tyre condition and pressures; remove any
mud lumps from treads. Hand protection should be worn. Use
mechanical aids to remove or replace wheel and tyre
assembly
|  |  |  | M | Check condition and tension of tracks (refer to operator’s |  |  |  | L | Operator
manual to determine correct sag range).
|  |  |  | H | Inspect for worn or missing teeth or worn cutting edges. |  |  |  | M | Operator
Check pins, bushes and connections for excessive wear.
Locking pins must be fitted. REFER to operator’s manual for
correct operating procedures for attachments. Quickhitches
used must be to AS7442:2008
|  |  |  | H | Check rams hoses and connections for splits leaks or |  |  |  | L | Operator
fractures. Wear eye and hand protection
14 | Entry and exit |  | Slipping and falls | M | Steps and ladders should be of a non-slip type. |  |  |  | L | Operator
Hand holds must be provided to assist operator to maintain 3
points of contact at all times while mounting or dismounting
tractor.
15 | Operator Position |  | Seating | M | Seat should be well-sprung and adjustable to allow operator |  |  |  | L | Operator
to maintain a comfortable operating position.
|  |  | Controls | M | All levers and gauges must be clearly identified, within easy |  |  |  | L | Operator
reach and be easily read. Preferred orientation should be
such that all needles are in vertical position during correct
operating conditions.
|  |  | Cabin (if fitted) | H | Exhaust must be placed so as to not allow fumes to enter |  |  |  | M | Operator
cabin
16 | Controls |  | Lights and alarms | M | Test all lights, indicators, horn and reversing alarm. |  |  |  | L | Operator
|  |  | Steering and brakes |  | Test steering both ways. Check braking and park brake
operation. Lock separated brake pedals together if travelling.
|  |  | Hydraulic controls | H | Test all hydraulic operations before loading bucket. |  |  |  | M | Operator
17 | Travel |  | Loss of Control | H | Do not travel at speeds which may cause control to be lost |  |  |  | M | Operator
over bumps, etc. Carry bucket as close to machine as
possible and racked back for visibility. Avoid driving over
obstacles, ditches, drains, etc which could affect control.
Check terrain before travelling. Avoid changing gear on
slopes. Travel down a slope in low gear.
|  |  | Overturning | E | Avoid sharp turns and travel across slope on a steep incline. |  |  |  | M | Operator
18 | Operation |  | Buried services | E | Ensure that all underground services have been identified |  |  |  | M | Contractor
and located before commencing to dig.
|  |  | Overturning | E | Outriggers must be extended and in contact with firm surface |  |  |  | M | Operator
before commencing to dig.
|  |  | Moving machinery, crush injury | E | Exercise care to not cause trench collapse when using |  |  |  | M | Operator
outriggers.
Avoid swinging loaded bucket with booms extended. Prevent
entry to swing area of boom and bucket when excavating.
Ensure that all persons are clear of boom before swinging.
Persons working near machinery in operation or areas where
traffic may be a hazard should wear high-visibility garments.
Do not load bucket in excess of working load limit.
|  |  | Overstressing of parts | H | Avoid stressing of parts when excavating rock, shale or other |  |  |  | M | Operator
tight material.
|  |  | Dust, falling objects, noise | E | Appropriate protective equipment should be used where |  |  |  | M | Operator
hazards may be encountered during operation. Head, eye
and hearing and foot protection may be required in some
work situations. Wear high-visibility garment when working
on roads or where other traffic will be encountered.
19 | Work Near overhead conductors |  | Electric Shock | E | Use an observer to warn of possible encroachment when |  |  |  | M | Contractor
working near power lines.
[5 empty] | Extra caution must be exercised when working on or near |  |  |  |  | Operator
uninsulated overhead conductors or other live electrical
equipment in elevated positions. Do not touch untested
electrical equipment.
[5 empty] | Any electrical equipment or installation, unless proven to be |  |  |  |  | Operator
de- energised, must be treated as being live.
Protective clothing and equipment worn and used by
electrical workers and their assistants must be of correct fit
and be in good condition.
All protective clothing and equipment must comply with
relevant AS/NZ Standards for the type of clothing or
equipment.
The following items should not be worn when working on or
near live electrical equipment-bracelets, rings, neck chains,
exposed metal zips, watches, metal spectacle frames, etc.
20 | Qld Rail |  | Train Traffic | E | When working on Qld Rail reserves, an 1800mm temporary |  |  |  | M | Contractor
barricade shall be erected prior to any other work being
carried out. Work shall not commence on Qld Rail sites until
a certified QR Lookout is on site and has undertaken
Worksite Safety Briefing. An exclusion zone of three metres
shall be maintained from overhead lines. If the exclusion
zone cannot be maintained, this WMS shall be approved in
writing by the Traction Power Engineer (QR). Operators
shall use designated walkways to cross tracks. Operators
shall ensure they step over, not on, tracks when crossing
them.
[5 empty] | No operators shall wear any red, yellow or green items of |  |  |  |  | Operator
clothing and that red, yellow and green items of plant are not
stored or used near the tracks. Operators shall maintain
continual vigilance for passing trains. Where possible /
practical, workers shall always face oncoming train traffic.
21 | Sub Station |  | Electric Shock | E | No Mechanical Excavation in a Sub Station is permitted |  |  |  | M | Contractor
unless Approval has been received by the appropriate
authority (e.g. – Energex Sub Station Services Manager).
Before performing excavation works full information relative
to the location of buried power & control cables must be
obtained. Machine Excavation shall only be performed when
a Safety Observer is monitoring the activity. The following
apparel must be considered, eye protection, footwear,
gloves, hearing protection, clothing, safety belts /harnesses,
head protection. Do not wear metallic objects unless suitably
insulated.
22 | Operation of mobile plant |  | Electric Shock | E | Check clearance under overhead electric wiring to maintain |  |  |  | M | Operator
safe distance.
Ensure that planned access to actual work area is not
obstructed.
[5 empty] | Liaise with site contact to find out who will be supervising the |  |  |  |  | Contractor/
[5 empty] | work on site, and obtain any specific instructions relating to |  |  |  |  | Operator
the job to be done. Use tail ropes on loads to prevent
swinging while being carried.
Ensure that cables and loads being slung do not come into
close proximity to electric wiring and installations. Wear Eye
protection, footwear, gloves, hearing protection, clothing,
safety belts /harnesses, head protection.
Persons who are not experienced electrical workers must not
come closer to low voltage overhead catenary wiring than the
safe approach distances-
• Using hand held tools- 0.5m
• Operation of crane or mobile plant- 3.0m
• Handling metal materials (scaffolding, guttering,
pipes, etc)-4.0m
• Handling non-conductive material (timber, ply, PVC,
etc)- 1.5m
• Driving or operating a vehicle- 0.6m.
If work cannot be carried out without encroaching within the
safe approach distances, the electrical authority should be
contacted to determine a safe method of carrying out the
work (including isolation of the circuit). Height warning bars
should be used where plant and vehicles are required to pass
under catenary wires and there is a risk of the plant or
vehicles contacting the wires. Physical protection (such as a
gantry or similar construction beneath the wires) to prevent
plant and vehicles contacting the wiring should be considered
if the work will be of a longer duration.
23 | Trenching Safety |  | Persons falling | H | A barricade at least 900mm high must be erected around a |  |  |  | M | Contractor/
[5 empty] | trench that is 1 metre or more deep unless it is not possible or |  |  |  |  | Operator
[5 empty] | only workers involved in the trench will be in the area; or |  |  |  |  | Operator
another form of barrier exists (such as excavated materials
near the trench).
|  |  | Trench Collapse and | E | Excavated material should not be placed less than 600mm |  |  |  | M | Operator
|  |  | Cave-in |  | from the edge of a trench to minimise risk of collapse due to the
weight of the spoil.
|  |  | Safe access and exit | H | Ladders must be provided no more than 9 metres apart in the |  |  |  | M | Contractor
area where work will be carried out. Safety footwear and head
protection must be worn
24 | Backfill |  | Persons falling | H | A barricade at least 900mm high must be erected around a |  |  |  | M | Contractor/
[5 empty] | trench that is 1 metre or more deep unless it is not possible or |  |  |  |  | Operator
only workers involved in the trench will be in the area; or
another form of barrier exists (such as excavated materials
near the trench). Stable freestanding barriers with no external
projections should be used. Ensure that adequate working
space is available- divert persons around or from area where
another form of barrier exists (such as excavated materials
near the trench). Stable freestanding barriers with no external
projections should be used. Ensure that adequate working
space is available- divert persons around or from area where
work area. Anyone entering the trench shall wear appropriate
PPE
25 | Craning Safety |  | Overloading of machinery | H | Only lift loads that are within the rated capacity of the machine. |  |  |  | M | Operator
Use only attachments approved for the particular machine to lift
loads.
|  |  | Overturning of machinery | E | Attach loads to be lifted to approved lift points on the boom, |  |  |  | M | Operator
dipper arm or bucket.
Travel at walking pace with load low to ground when
transporting load. Avoid rapid rotation of machine to minimise
uncontrolled swinging of load. Use tag lines attached to both
ends of pipes, etc, to control swinging of load. Wear hand and
foot protection. Must have competency to undertake task.
26 | Ripper |  | Sharp edges | H | Exercise care when handling ripper attachment to avoid sharp |  |  |  | M | Operator
edges and nicks on cutting tooth and edges of tine.
|  |  | Flying objects | H | Stand to side or rear when using tools to remove teeth from |  |  |  | M
|  |  | Noise |  | attachments. Hearing protection may be required when
operating ripper from non- insulated operator position. Wear
gloves when handling rough or sharp objects. Operator also
must wear eye and hearing protection.
27 | Rock Breaker/Hammer |  | Sharp edges | H | Exercise care when handling tool bit of attachment to avoid |  |  |  | M | Operator
sharp edges and nicks on cutting faces of tool.
|  |  | Flying objects | H | Refer to manufacturer’s manual to determine 85dB radius, and |  |  |  | M
|  |  | Noise |  | ensure that all persons within this zone are issued with and
wear appropriate PPE. Wear gloves when handling rough or
sharp objects.
Operator also must wear eye and hearing protection.
28 | Grab |  | Falling objects | H | Keep all persons clear of grab when grasping objects such as |  |  |  | M | Operator
rocks which may easily dislodge from grab when lifted.
Ensure that all persons are clear when lifting long objects (such
as tree parts, poles, etc). Always perform test lift to check
security of object in jaws. Do not lift higher than necessary to
load objects into truck, etc
29 | Compactor Wheel/drum |  | Falling objects | H | Ensure that unit is secured from falling when detached from |  |  |  | M | Operator
boom.
Chock or pack compactor wheel to prevent movement when
transporting. Keep hands and clothing, etc, well clear of
|  |  | Moving parts, pinch points | H | compactor wheel when in operation to prevent clothing, etc, |  |  |  | M
catching on feet.
Ensure that wheel is prevented from movement before
detaching hitch. Lay compactor attachment down before
detaching from hitch. Keep all persons well clear of moving
compactor wheel. Pack or chock to prevent moving.
30 | Auger |  | Falling objects | H | Ensure that unit is secured from falling when detached from |  |  |  | L | Operator
boom. Chock or pack auger spiral to prevent movement when
transporting. Ensure that auger spiral is securely attached to
motor unit before lifting. Ensure that underground services are
|  |  | Harmful Contact or | H | located before commencing to drill, and that areas where holes |  |  |  | M | Contractor
|  |  | exposure |  | are to be drilled are free from hazards.
Ensure that all persons are kept well clear of auger when in
|  |  | Moving parts | H | operation. Operator must stop auger if anyone approaches the |  |  |  | M | Operator/
[5 empty] | hole for any reason. Ensure auger is completely stopped before |  |  |  |  | Contractor
|  |  | Flying objects | H | attempting to clean spiral. Always use bar or tool with handle |  |  |  | M | Operator
to clean dirt, etc, from auger.
Stand to side or rear when using tools to remove teeth from
attachments. Avoid contact with edges which may become
|  |  | Sharp edges | H | sharp during drilling. Lay auger attachment down before |  |  |  | M | Operator
detaching from hitch.
Check that pins are secured. Do not start to drill unless area
has been declared safe for drilling. Barricade area where
drilling is carried out to exclude all persons except those
involved in job. Keep hands clear of auger. Wear eye
protection. Wear cut-resistant gloves.
31 | Operation of Tipper/Dump Truck |  | Moving parts |  | Check all fluid levels, including oils, water, hydraulics and |  |  |  |  | Operator
| -Pre Start |  | Harmful Exposure |  | battery fluid. Carry out operating check of all lights, flashers
| -General Precautions |  |  |  | and warning signals. Check all tyres for correct pressure, wear
or damage to tread or casings. Check all parts for loose or
missing bolts, screws or fasteners.
Visually check condition of chassis, body and suspension
components. Inspect hydraulic hoses, rams, etc, for leaks or
damage. Make sure all personnel are clear of machine before
starting. Persons operating plant on sites must wear PPE as
|  |  | Musculo-Skeletal injury |  | required on site. Persons working in vicinity of plant or vehicles |  |  |  |  | Operator
must wear Hi-vis garments. Use orange flashing lamp and
reversing beeper to warn of hazard from plant. Pinch points
and nip points should be highlighted with appropriate warning
signs posted advising of danger.
Always sound warning to advise others of intention to operate
vehicle.
Always maintain 3 points of body contact when entering or
leaving cabin. Adjust seat to suit operator stature, and adjust
|  |  | Collision |  | and fasten seat belt. Check condition of, and adjust mirrors to |  |  |  |  | Operator
provide good rear and side vision. Ensure that park brake is
engaged, and transmission is in neutral.
|  |  | Overturning |  | Allow engine to warm up at low idle for specified time (at least 5 |  |  |  |  | Operator/
[5 empty] | mins.). Cycle all controls to allow warm oil to circulate through |  |  |  |  | Contractor
entire system. Recheck transmission and hydraulic fluid levels,
top up if low reading.
Ensure that flashing lights, warning signals, reversing beepers,
etc, are in operating order and clearly visible and audible
before operating truck. Check that all persons and vehicles are
clear of truck before moving off.
Limit speed on unmade terrain and haul roads to avoid loss of
control. Avoid travel over rough terrain and depressions which
could tilt vehicle. Keep safe distance from edge of roads and
excavations, pits, etc. Keep rear wheels of vehicle at safe
distance from bank when dumping. Do not raise body unless
vehicle is standing on firm, stable ground. Wear foot protection
and hi-visibility vest or shirt. Keep persons clear of area where
truck or trailer is tipping for a distance at least equal to the
height of the body when fully raised. Do not carry objects in
hands when entering or leaving cabin.
32 | Tarpaulins |  | Load Shifting | H | Tarpaulins should only be used for dust or weather protection |  |  |  | M | Operator
or to cover loose loads that maybe affected by air flow during
transport. Tarpaulins must be securely lashed to prevent
movement
33 | Maintenance |  | Burns | H | Allow engine to cool before removing radiator cap. |  |  |  | M | Operator
|  |  | Over-exertion/strain injury |  | Rear tyres may be water-filled as ballast- always have valve
stem at top position to check pressure or inflate tyre. Place
|  |  | Crush injury from falling | H | valve at bottom position to drain water from tyre. |  |  |  | M | Operator
|  |  | object |  | Use mechanical aid to remove or replace counterweights.
Relieve stored energy in hydraulic and pneumatic systems
before servicing. Keep clear of moving parts.
Wear eye, hearing, body, hand and foot protection.
34 | Repairs etc, to buckets |  | Replacement of teeth | M | Place bucket on firm, stable, level surface to carry out work. |  |  |  | L | Operator
Ensure that engine is switched off and hydraulic pressure is
relieved before replacing teeth on bucket attached to
excavator.
Clean excess mud and soil from bucket before replacing teeth.
[5 empty] | Ensure that replacement teeth are compatible with the bucket. |  |  |  |  | Operator
Check that hand tools to remove damaged or worn teeth are in
[5 empty] | good condition. |  |  |  |  | Operator
Ensure that replacement teeth are firmly locked in position
before digging.
35 | On-site refuelling |  | Fire Risk | E | Eliminate ignition sources in vicinity of refuelling operations. |  |  |  | M | Contractor/
[5 empty] | Switch off engines of plant and vehicles before commencing |  |  |  |  | Operator
refuelling. Do not leave pump or fuel hose unattended during
refuelling
Restrict entry to site to persons directly involved in refuelling
operation. Do not overfill fuel tanks, and clean up spills or leaks
|  |  | Inhalation of vapours, Dry Skin, Dermatitis Irritation to eyes | E | immediately. Avoid contact with fuels and oils during refuelling. |  |  |  | M | Operator
Decanting and mixing of fuel should be carried out in a well
ventilated area. Provide earthing straps to eliminate build up of
static electricity.
Avoid direct contact with petrol and fuels on skin.
Avoid splashing of fuel, and avoid getting petrol or fuel in eyes.
|  |  | Environmental Risk | E | Prevent entry of fuels and oils into drains or waterways. |  |  |  | M | Operator
Absorb spill with oil-sorb or pads, and place into sealable
container. Dispose of waste at a roved chemical waste
disposal facility.
Suitable fire extinguisher must be carried on vehicle.
Emergency PPE and spill kit must be carried with placarded
loads. No smoking or ignition sources. Eliminate static
electricity sources. Wear PVC gloves and apron. Wear eye
protection at all times
36 | Parking |  | Stability | M | Park Excavator on level ground if possible. |  |  |  | L | Operator
Position machine “up and down” the slope if parking on sloping
ground. Apply handbrake, place transmission in neutral or
“park” position.
Lower attachments fully and release pressure from hydraulic
lines. Switch off engine and remove keys before leaving
machine unattended. Do not leave loader unattended with
engine running.
37 | Transport |  | Loading/Unloading | H | As per step 1-6 & 12 |  |  |  | M | Operator
38 | Leave Site |  | Traffic Road Safety | M | As per step 7 |  |  |  | L | Operator
39 | Accidents and injuries |  | Reporting of accidents | E | All drivers should be familiarised with procedures to follow in |  |  |  | M | Operator/
|  |  | Injuries |  | case of an accident. All accidents, no matter how minor, must |  |  |  |  | Contractor (onsite
[5 empty] | be reported. Suitable first aid kits must be provided in all |  |  |  |  | accidents or injuries
[5 empty] | vehicles |  |  |  |  | only)
SAFE WORK METHOD STATEMENT & RISK ASSESSMENT
Precautions
| The following precautions are to be observed in areas where |  | Operation of |  |  |  | Maintenance of
| these procedures are carried out. |  | plant |  |  |  | plant
COMMENTS OR REVIEW |  |  |  |  | AMENDMENTS
Operator Signed: |  |  | Date: |  | Operator Signed: |  |  |  | Date:
Contractor Signed: |  |  | Date: |  | Contractor Signed: |  |  |  | Date:
WORK METHOD STATEMENT REVIEWED AND ACCEPTED BY CONTRACTOR AND OPERATOR
Operator Signed: |  |  | Date: |  | Operator Signed: |  |  |  | Date:
Contractor Signed: |  |  | Date: |  | Contractor Signed: |  |  |  | Date: